## Sheet1
Backlog Item | Owner | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11
Documentation |  | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Final Design Document | Will | bar: Day 1
Change Impact Analysis | Will | bar: Day 1
Scrum Minutes | Will and Jamie | Day 1: 0.5
Final Test Case | Will | bar: Day 1
Final Code |  | 16 | 16 | 15 | 14 | 14 | 13 | 13 | 12 | 6 | 4 | 3
Final Code Completion | Will and Jamie | 16 | 16 | 15 | 14 | 14 | 13 | 13 | 12 | 6 | 4 | 3
| Estimated Hours | 19.5 | 16 | 15 | 14 | 14 | 13 | 13 | 12 | 6 | 4 | 3
| Working Hours* Until Sprint End | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2
Working Hours = 2 hours per day
INFT 2100 Project Management 702
Scrum Assignment "Game of Life"
Now known as “Ant Lions”
Sprint 2 Backlog and Sprint 2 Burndown
Owners:
James Curnew
William Matheson
Benjamin Allen
Isaac Benoit
Based on: http://www.invisible-city.com/sharon/2008/09/sprint-heartbeat-visual-task-tracking.html